## Project issuse
Unclosed Projects that are impacting the profitability of Sales Contracts and the company profitability
No. | Contract Names | Contract signing date | Remark
1 | CBE 10 Bulk Deposit | 2023-04-25 | Project is not closed. It has been 3 years and 6 month since the contract is signed and not closed yet We have been extending the advance and perfromance bond guarrantee since the contract signing date
2 | CBE Kiosk | 2023-12-11 | Project is not closed. It has been 2 years and 10 months since the contract is signed and not closed yet. We have been extending the advance and perfromance bond guarrantee since the contract signing date. Uncollected payment 5.5M
3 | CBE CVM | 2024-07-26 | Project is not closed. It has been almost 2 yrs and 3 months since the contract is signed and not closed yet. We have been extending the advance and perfromance bond guarrantee since the contract signing date.
4 | Dashen Kiosk | 2025-08-22 | Project not closed. UAT signed October 7, 2026 excluding the account opening scope. It has been 1 year & 2 months since the contract is signed and not closed. Contract delivery schedule is 60 days from contract signing. Penalty is counting: Unitl today delay of 355 days. This has already passed the 10% penalty. 10% penalty: 4.8M Birr Uncollected payment: 34M Birr
5 | Awash Bank Card Perso | 2023-11-01 | Project not closed. Installation and training payment not collected uncollected amount: 270K The Personalization solution is awarded to Toppan gravity recently. The bank said they will release this payment as the personalizatoin solution project progressed

## October 9 2026
N&S Division
S.N | Customer Name | Item | Issue | Current Status | Next Action | Challenge
1 | OCC | Firewall | the advance payment is still pending | we are folowuping
| CBE | SecureSync | vendor production | AWB received
| NBE | Switches and AP | * Palletized for shipment * contract extension requested | * waiting shipment docs
S&S Division
Issue
S.N. | Customer Name | Item | Issue | Current Status | Next Action | Challenge
1 | Awash Bank | NAS | 1. The delivered license is not visible on the customer portal, and the support entitlement does not cover the required five-year period. 2. Awash Bank has requested official authorization for the training center, which is currently renewing its authorization. | The Huawei team is working to resolve the license visibility and support entitlement issues. | Follow up with Huawei to ensure the license is visible, the support period is corrected to five years, and the training center's authorization is provided. | Delays in resolving the license and support issues, along with the pending training center authorization.
2 | GIC | Microsoft Licenses | We attempted to deliver the Microsoft licenses, but the GIC account was registered with Zambia as its location. Since the location cannot be changed, the licenses cannot be delivered through the existing account. | GIC needs to create a new account with the correct location to proceed with license delivery. | Follow up with GIC to ensure a new account is created with the correct location. | License delivery is on hold until the new account is created.
3 | COOP Bank | Tape Library | Upon delivery, it was discovered that the labels on the tape library did not meet the customer's requirements. | We are working on replacing the labels to meet the customer's specifications. | Follow up to ensure the replacement labels are provided and meet the customer's requirements. | Delay in providing compliant labels.
4 | CBE | Tape Library and SAN Training | The training payment is pending due to the bank's budget constraints. | Pending resolution of the bank's budget issue. | Follow up with the bank regarding budget availability and the training payment. | The bank's budget constraints are delaying the training payment.
4 | CBE | SAN firmware Update | firmware download issue | * firmware downloaded * firmware update preventive maintenance ticket opened * Work Order assigned to BIOS | Upgrading the firmware by field engineer based on the Work Order
DCF SS Division
S.N | Customer Name | Item | Issue | Current Status | Next Action | Challenge
1 | PPS | UPS | the PO from customers are limited | we have submitted a letter for the second time on October 16th, 2026. | we will visit them to discuss the issue in person
PCBE Issues
S.N | Customer Name | Item | Issue | Current Status | Next Action | Challenge
1 | CBE | Digital Branch (Kiosk) | the bank resolved the API issue for the 2 services( Waterbill and Fund transfer) Accordingly sedco already worked on it as change request (CR) but without payment and CBE team didn't test it yet. In addition the Bank didn't respond to our notificaton letter regarding the CR's and their associated cost. | The bank has requested for the 2 services to go live (Waterbill and Fund transfer) and it was expected to go live But the bank hold the fund transfer with API issue and the water bill payment due to connectivity issues . We provided a separate HLD & LLD documents for each services as per the banks request | 1. Closely follow up the with bank and Sedco team to resolve the connectivity and API issue for water bill and fundtransfer (Phase 1 2. submit a commitment letter for the remaining scope of projects and request our payment after the kiosk (phase 1) go live 3. Push the bank to approve the CR documentations and their willingness on the associated costs of CRs.
|  | CVM | There is an issue on mobile booking | We are waiting for the bank to provide us with the error log from their side inorder to investigate and resolve the issue | Follow up with the bank to share with us the log file and resolve the issue promptly
|  | Bulk deposit (10Qty) | There is an issue on SoftWare. All 10 machines are offline when they check from the backend | Hardware confirmation is not sent from inspection team. They mentioned that they would like to see all machines functional and the Software also to be tested. | Push the inspection team to send the confirmation for Hardware and release our payment for the delivered Hardware. Then resolve the Software issue
2 | Dashen Bank | Supply, installation, Training, Support and maintenanace of 10 self service Kiosk | the project team needs to share with us the API's for the development and the remaining bill payments | The banks contract team has sent the technical proposal for their project team but the project team has share one bill payment and we are waiting for the bank to share with us. | Our project team planned Implementation scheduled to be completed by the end of June, 2026.
|  | Instant Issuance – Support & Maintenance | Thales is requesting payment for the 2024 and 2025 S&M Purchase Orders. However, there is no active support agreement in place, and the bank is requesting system changes to UAT for PCI DSS compliance. Thales has indicated challenges in providing support without a valid agreement. | No active SLA agreement exists between Dashen Bank and Moti. The license is valid until July 2026. A PO has been issued for 2024 and 2025. | Explain to the bank that the Dexxis license has expry date, Follow up with the bank and Thales to clarify the support arrangement and resolve the payment issue.
3 | Awash Bank | Card Personalization Machine | The machines have been delivered to the bank but are not operational because the bank has not yet purchased the personalization solution. Payment for training and installation remains on hold. | The bank is working on procuring the required solution and has requested us to wait to collect the remianing payment. | We are planning to submit a letter rquesting for the release of our payment before the end of this budget year.
|  | PIN Mailer | The bank rejected defective PIN mailers and terminated the contract. The stock remains in our warehouse and cannot currently be utilized for other banks. | Over 300,000 units remain in stock. The bank collected 19,500 units for testing and they used it successfully. | Engage the bank to acceptance of the remaining stock.
4 | Siinqee Bank | Price Adjustment – PIN Mailer & Card | A price adjustment request was submitted for PIN mailers; however, the bank rejected the proposal. A reconsideration letter has been submitted. | Awaiting response after submitting the reconsideration request.
5 | Abay Bank | TOMS SLA | The TOMS warranty expired on April. The bank didn't pay for TOMS SLA and there is no Active SLA. by considering partnership Newland team extended the TOMS license up to May end | We've informed the bank about the expiry of TOMS warranty and requested for SLA with submitted price. Accordingly the bank requested for discount and draft SLA agreement. We've prepared a draft SLA agreement and P&L Summary | Request Newland team for Discount and share the draft SLA agreement with the Bank after the Legal team and PS team review.
|  | POS | Newland shipped a POS with 0.3MP camera, which is under spec as the POS was supposed to come with 2mp camera. | The bank didn't notice the issue and has accepted the POS | Discussion is needed on how to commence the camera repalcement. The Newland team provided cameras during their visit in Addis Ababa and they also provided a training to our workshop team on how to replace the camera.
6 | Demo kiosk |  | Sedco teams are requesting for the LC extenshion and to ship the kiosk without the camera and to ship the camera separatly. The LC expires on May 21, 2026 | The LC extended and agreed to proceed with DHL for shipment. However due to Eid holidays we only will get update by next week | Follow up the shipment status by DHL
6 | Demo kiosk |  | Sedco teams are requesting for the LC extenshion and to ship the kiosk without the camera and to ship the camera separatly. The LC expires on May 21, 2026 | Follow up with our logistics and sedco team for the shipment